## Task Table
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 8 | 12 | 16
B | Develop marketing strategy |  | 8 | 16 | 24
C | Design brochure | A | 2 | 6 | 10
D | Develop product prototype |  | 0 | 0 | 0
D1 | Requirements analysis | A | 4 | 6 | 8
D2 | Software design | D1 | 10 | 20 | 30
D3 | System design | D1 | 12 | 20 | 24
D4 | Coding | D2, D3 | 16 | 32 | 48
D5 | Write documentation | D4 | 6 | 8 | 10
D6 | Unit testing | D4 | 16 | 32 | 48
D7 | System testing | D6 | 16 | 32 | 48
D8 | Package deliverables | D5, D7 | 4 | 12 | 20
E | Survey potential market | B, C | 16 | 20 | 24
F | Develop pricing plan | D8, E | 24 | 32 | 40
G | Develop implementation plan | A, D8 | 16 | 20 | 24
H | Write client proposal | F, G | 8 | 32 | 56
| Hourly Rate: | 31.51

## Gannt
MSDS Assignment 2
Graham Lovell | [5 empty] | Best Case | [5 empty] | Start |  |  |  |  | Dummy Arc | [6 empty] | End
ACTIVITY | PLAN START | EXPECTED PLAN DURATION | EXPECTED PLAN DURATION | EXPECTED PLAN DURATION | Hours
[5 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108
Describe product | 0 | 8 | 12 | 16 | bar: Hours 0 to Hours 7
Develop marketing strategy | 0 | 8 | 16 | 24 | bar: Hours 0 to Hours 7
Design brochure | 8 | 2 | 6 | 10 | bar: Hours 8 to Hours 9
Develop product prototype (Dummy Arc) | 8 | 0 | 0 | 0 | bar: Hours 8 to Hours 75
Requirements analysis | 8 | 4 | 6 | 8 | bar: Hours 8 to Hours 11
Survey potential market | 10 | 16 | 20 | 24 | bar: Hours 10 to Hours 25
Software design | 12 | 10 | 20 | 30 | bar: Hours 12 to Hours 21
System design | 12 | 12 | 20 | 24 | bar: Hours 12 to Hours 23
Coding | 24 | 16 | 32 | 48 | bar: Hours 24 to Hours 39
Write documentation | 40 | 6 | 8 | 10 | bar: Hours 40 to Hours 45
Unit testing | 40 | 16 | 32 | 48 | bar: Hours 40 to Hours 55
System testing | 56 | 16 | 32 | 48 | bar: Hours 56 to Hours 71
Package deliverables | 72 | 4 | 12 | 20 | bar: Hours 72 to Hours 75
Develop pricing plan | 76 | 24 | 32 | 40 | bar: Hours 76 to Hours 91
Develop implementation plan | 76 | 16 | 20 | 24 | bar: Hours 76 to Hours 99
Write client proposal | 100 | 8 | 32 | 56 | bar: Hours 100 to Hours 107

## Directed Graph
0
1
Describe product (8)
Develop marketing strategy (8)
2
4
Requirements analysis (4)
Design brochure (2)
3
Survey potential market (16)
Coding (16)
Software Design (10)
System Design (12)
5
6
Unit Testing (16)
Write Documentation (6)
7
System Testing (16)
8
Package Deliverables (4)
8
10
Write client proposal (8)
Develop pricing plan (24)
Develop implementation plan (16)